## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a data engineer, I want to collect and preprocess imaging and EHR data so that it can be used for model training. | Must Have | None | Team B | Completed
Sprint 2 | Sprint 2 | US02 | As a developer, I want to enhance medical images using GenAI so that clinicians can interpret them more easily. | Must Have | US01 | Team B | Completed
Sprint 3 | Sprint 3 | US03 | As a clinical documentation assistant, I want to generate patient clinical notes automatically from structured data. | Should Have | US01 | Team B | Completed
Sprint 3 | Sprint 3 | US04 | As a system, I want to map EHR data to ICD-10 codes automatically to reduce manual errors. | Should Have | US03 | Team B | Completed
Sprint 4 | Sprint 4 | US05 | As a developer, I want to integrate GenAI models with an EHR interface (Streamlit/Django) for doctors to use easily. | Must Have | US02, US03 | Both Teams | Completed
Sprint 4 | Sprint 4 | US06 | As a QA engineer, I want to test, deploy, and document the integrated EHR system to ensure it works reliably. | Could Have | US05 | Both Teams | In Progress

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours)
US03 | T01 | Prepare imaging and clinical data for AI model training and application | 2025-10-15 | 2025-10-28 | Team B | Data Collection and Preprocessing | Completed | 6
US03 | T02 | Use GenAI to enhance image quality and support diagnosis | 2025-10-29 | 2025-11-11 | Team B | Medical Imaging Enhancement | Completed | 7
US04 | T03 | Automate routine documentation and coding tasks using GenAI | 2025-11-12 | 2025-09-25 | Team B | Clinical Note Generation &amp; ICD-10 Coding Automation | Completed | 8
US04 | T04 | Deploy and integrate the enhanced EHR features into clinical environments | 2025-11-26 | 2025-12-10 | Team B | Integration and Deployment | Completed | 4

## Daily Stand-up
Sprint | Day | Impediments | Action Taken
Sprint 3 | Day 2 | Limited access to Azure OpenAI resources | Used free pretrained HuggingFace model as alternate solution
Sprint 3 | Day 3 | Clinical notes not mapping correctly to ICD-10 codes | Debugged schema and fixed data type mismatch
Sprint 3 | Day 4 | Slow performance in model inference | Implemented caching for patient data and reduced latency
Sprint 3 | Day 5 | None | Proceeded with integration testing successfully

## Sprint Retrospective
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 3 | 25-Sep-2025 | 02-Oct-2025 | Team B | Use GitHub issues for daily task tracking | Collaborating effectively during testing and debugging | Delaying commits till last day | Collaborating during testing and debugging | Shared daily updates and improved communication
2 | Sprint 3 | 25-Sep-2025 | 02-Oct-2025 | Team B | Validate dataset early | Maintaining consistent documentation | Using unverified sample data | Maintaining consistent documentation | Dataset verification checklist created
3 | Sprint 3 | 25-Sep-2025 | 02-Oct-2025 | Team B | Encourage peer code review | Conducting code reviews | Manual merging without review

## Defect Log
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Team B | 12-Sep | Model not detecting images properly | Sprint 2 | Team B | Functional | Adjusted image preprocessing | 13-Sep | Closed | Verified
2 | Team B | 19-Sep | ICD-10 code generation failed for certain cases | Sprint 3 | Team B | Logical | Updated disease-code mapping | 20-Sep | Closed | Validated
3 | Team B | 25-Sep | Output visualization not displaying results | Sprint 4 | Team B | UI | Fixed frontend rendering script | 26-Sep | Closed | Stable Team pr